## Product Backlog (User Stories)
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a founder, I want to submit a startup idea in the React UI so that validation research can begin | Must Have | None | Member 4 | Completed
Sprint 1 | Sprint 1 | US-02 | As a backend system, I want a FastAPI /api/search endpoint so that client requests trigger web search workflows | Must Have | US-01 | Member 4 | Completed
Sprint 1 | Sprint 1 | US-03 | As an intelligence agent, I want 4-vector query decomposition (domain, problem, solution, audience) to maximize search relevance | Must Have | US-02 | Member 1 | Completed
Sprint 1 | Sprint 1 | US-04 | As an intelligence agent, I want a dual Tavily API and DuckDuckGo search fallback so that web research never fails offline | Must Have | US-03 | Member 1 | Completed
Sprint 2 | Sprint 2 | US-05 | As an orchestrator, I want parallel multi-agent dispatch via asyncio.gather so that market and competitor analyses run concurrently | Must Have | US-04 | Member 1 | Completed
Sprint 2 | Sprint 2 | US-06 | As a market analyst, I want to classify the venture's industry and calculate TAM/SAM/SOM market opportunity | Must Have | US-05 | Member 2 | Completed
Sprint 2 | Sprint 2 | US-07 | As a product strategist, I want target customer segmentation with needs and pain points extracted from market data | Must Have | US-06 | Member 2 | Completed
Sprint 2 | Sprint 2 | US-08 | As a competitive analyst, I want to discover direct and indirect competitors from web search results | Must Have | US-05 | Member 3 | Completed
Sprint 2 | Sprint 2 | US-09 | As a competitive analyst, I want to extract competitor pricing and key features to build a comparison matrix | Must Have | US-08 | Member 3 | Completed
Sprint 2 | Sprint 2 | US-10 | As a founder, I want to identify unmet market gaps and white spaces to differentiate my product | Must Have | US-09 | Member 3 | Completed
Sprint 2 | Sprint 2 | US-11 | As a developer, I want resilient domain-aware heuristic fallbacks so that the orchestrator never returns 500 errors | Must Have | US-05 | Member 1 | Completed
Sprint 2 | Sprint 2 | US-12 | As a founder, I want an interactive React dashboard to view market opportunity, customer segments, and competitor matrix | Must Have | US-05 | Member 4 | Completed
Sprint 3 | Sprint 3 | US-13 | As a technical founder, I want technical feasibility assessment and architecture complexity scoring | Should Have | US-06 | Member 2 | Completed
Sprint 3 | Sprint 3 | US-14 | As an investor, I want scientific literature benchmarking and empirical feasibility validation | Should Have | US-13 | Member 2 | Completed
Sprint 3 | Sprint 3 | US-15 | As a founder, I want regulatory risk mapping and compliance approval pathways (GDPR, HIPAA, FDA) | Should Have | US-14 | Member 2 | Completed
Sprint 4 | Sprint 4 | US-16 | As a founder, I want an autonomous 4-quadrant SWOT matrix (Strengths, Weaknesses, Opportunities, Threats) | Must Have | US-10 | Member 1 | Completed
Sprint 4 | Sprint 4 | US-17 | As a risk manager, I want multi-factor risk analysis across 6 domains (Technical, Market, Financial, Competition, Operational, Adoption) | Must Have | US-16 | Member 1 | Completed
Sprint 4 | Sprint 4 | US-18 | As an investor, I want risk items to include severity ratings, business impact statements, and actionable mitigations | Must Have | US-17 | Member 1 | Completed
Sprint 4 | Sprint 4 | US-19 | As an orchestrator, I want SWOT and Risk analysis integrated into the central ValidationResponse contract | Must Have | US-18 | Member 1 | Completed
Sprint 4 | Sprint 4 | US-20 | As a user, I want SWOT quadrant cards and Risk & Mitigation tables rendered on the React dashboard | Must Have | US-19 | Member 4 | Completed
Sprint 4 | Sprint 4 | US-21 | As a founder, I want an executive PDF validation dossier generator to download and share with stakeholders | Should Have | US-20 | Member 4 | Completed

## Sprint Tasks & Burndown
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
[7 empty] | TOTAL REMAINING (HOURS) | 72 | 72 | 65 | 55 | 42 | 32 | 23 | 17 | 13 | 8 | 5 | 2 | 0 | 0 | 0
US-01 | T-101 | Design React idea submission input form with validation | 2026-08-03 | 2026-08-05 | Member 4 | Frontend UI | Completed | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-102 | Configure Axios API client and error toast notifications | 2026-08-04 | 2026-08-06 | Member 4 | Frontend Integration | Completed | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-103 | Setup FastAPI project structure and CORS middleware | 2026-08-03 | 2026-08-04 | Member 4 | Backend API | Completed | 6 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-104 | Implement /api/search endpoint with Pydantic request models | 2026-08-05 | 2026-08-07 | Member 4 | Backend API | Completed | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-105 | Implement 4-vector query decomposition algorithms | 2026-08-04 | 2026-08-07 | Member 1 | AI Engineering | Completed | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-106 | Write vector query unit tests and regex validations | 2026-08-07 | 2026-08-09 | Member 1 | Testing | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-107 | Integrate Tavily Search API client with credential manager | 2026-08-05 | 2026-08-08 | Member 1 | Integration | Completed | 8 | 8 | 8 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-108 | Build DuckDuckGo HTML scraping fallback for offline stability | 2026-08-08 | 2026-08-11 | Member 1 | Resilience | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-109 | Execute test_search_api.py test suite (5 tests) | 2026-08-11 | 2026-08-13 | Member 4 | Quality Assurance | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0
US-01 | T-110 | Sprint 1 integration review and staging branch merge | 2026-08-13 | 2026-08-14 | Member 1 | DevOps/Review | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0
SPRINT 2 BACKLOG
[7 empty] | TOTAL REMAINING (HOURS) | 114 | 114 | 105 | 95 | 84 | 69 | 54 | 43 | 30 | 20 | 12 | 6 | 1 | 0 | 0
US-05 | T-201 | Design central orchestrator architecture and pipeline flow | 2026-08-17 | 2026-08-19 | Member 1 | Architecture | Completed | 8 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-202 | Implement asyncio.gather parallel agent execution stream | 2026-08-19 | 2026-08-21 | Member 1 | Backend Engine | Completed | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-203 | Build industry taxonomy classifier and TAM/SAM/SOM formulas | 2026-08-17 | 2026-08-20 | Member 2 | Data Modeling | Completed | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-204 | Extract emerging market trends from live search evidence | 2026-08-20 | 2026-08-22 | Member 2 | NLP/AI | Completed | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-205 | Develop customer persona, user needs, and pain points extractor | 2026-08-21 | 2026-08-24 | Member 2 | AI Engineering | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-206 | Implement direct vs. indirect competitor classification heuristics | 2026-08-17 | 2026-08-20 | Member 3 | Algorithm Dev | Completed | 12 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-207 | Build competitor feature extraction and pricing parser | 2026-08-20 | 2026-08-23 | Member 3 | NLP/Extraction | Completed | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-208 | Synthesize competitor matrix comparison and market white spaces | 2026-08-23 | 2026-08-26 | Member 3 | Competitive Intel | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0
US-11 | T-209 | Construct zero-crash domain heuristic fallbacks in orchestrator | 2026-08-24 | 2026-08-27 | Member 1 | Resilience Eng | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0
US-12 | T-210 | Develop React components (MarketAnalysis, CompetitorAnalysis) | 2026-08-22 | 2026-08-26 | Member 4 | Frontend UI | Completed | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-211 | Connect POST /api/validate route and verify end-to-end integration | 2026-08-26 | 2026-08-28 | Member 4 | Full-Stack | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0
US-05 | T-212 | Run test_orchestrator.py and test_competitor_analysis.py suites | 2026-08-27 | 2026-08-29 | Member 1 | Testing | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0
SPRINT 3 BACKLOG
[7 empty] | TOTAL REMAINING (HOURS) | 64 | 64 | 60 | 54 | 43 | 33 | 28 | 25 | 19 | 15 | 11 | 8 | 3 | 0 | 0
US-13 | T-301 | Design technical feasibility Pydantic schema and scoring logic | 2026-08-31 | 2026-09-02 | Member 2 | Architecture | Completed | 8 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-302 | Model engineering complexity, tech stack risks, and scalability tiers | 2026-09-02 | 2026-09-04 | Member 2 | Backend Eng | Completed | 10 | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-303 | Build scientific literature search heuristics and citation parser | 2026-09-01 | 2026-09-04 | Member 2 | Data Sci | Completed | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-304 | Formulate empirical feasibility confidence score calculations | 2026-09-04 | 2026-09-07 | Member 2 | Algorithms | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-305 | Map regulatory approval pathways across Healthcare/FinTech/Drones | 2026-09-03 | 2026-09-06 | Member 2 | Compliance Eng | Completed | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-306 | Incorporate regulatory disclaimers and compliance risk matrices | 2026-09-06 | 2026-09-09 | Member 2 | Backend Dev | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0 | 0
US-13 | T-307 | Write server/tests/test_deep_validation.py test cases (5 tests) | 2026-09-08 | 2026-09-11 | Member 2 | Testing | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0
US-13 | T-308 | Integrate deep validation vectors into orchestrator pipeline | 2026-09-10 | 2026-09-12 | Member 1 | Orchestration | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0
SPRINT 4 BACKLOG
[7 empty] | TOTAL REMAINING (HOURS) | 92 | 92 | 89 | 83 | 77 | 66 | 60 | 55 | 45 | 34 | 21 | 9 | 2 | 0 | 0
US-16 | T-401 | Design 4-quadrant SWOT matrix Pydantic schema (SWOTAnalysis) | 2026-09-14 | 2026-09-16 | Member 1 | Schema Design | Completed | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-402 | Implement Strengths & Weaknesses heuristic and LLM extraction | 2026-09-15 | 2026-09-18 | Member 1 | AI Agent Dev | Completed | 10 | 10 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-403 | Cross-reference competitor gaps to generate Opportunities & Threats | 2026-09-17 | 2026-09-20 | Member 1 | AI Agent Dev | Completed | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-404 | Build 6-domain Risk Analysis taxonomy and RiskItem schema | 2026-09-16 | 2026-09-19 | Member 1 | Data Modeling | Completed | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-405 | Implement severity rating, business impact, and mitigation generator | 2026-09-19 | 2026-09-22 | Member 1 | AI Agent Dev | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-406 | Integrate swot_risk_agent into run_orchestrator pipeline | 2026-09-21 | 2026-09-23 | Member 1 | Orchestration | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0
US-19 | T-407 | Harden competitor classification heuristics for clean pipeline pass | 2026-09-22 | 2026-09-24 | Member 1 | Bug Fix/Refactor | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0 | 0
US-19 | T-408 | Author test_swot_risk.py and execute 59-test regression suite | 2026-09-23 | 2026-09-24 | Member 1 | Testing | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0 | 0
US-20 | T-409 | Develop React SWOT quadrant grid and interactive Risk table UI | 2026-09-21 | 2026-09-24 | Member 4 | Frontend Dev | Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0
US-21 | T-410 | Implement investor validation report PDF generation engine | 2026-09-23 | 2026-09-25 | Member 4 | Reporting | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 1 | 0 | 0
US-19 | T-411 | Submit Pull Request #18, resolve staging merge, and update docs | 2026-09-24 | 2026-09-25 | Member 1 | DevOps/Release | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 1 | 0 | 0

## Daily Impediments Log
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Tavily API rate limits triggered 429 status code during repeated query test runs | Implemented automatic fallback to DuckDuckGo search parser with exponential retry logic.
Sprint 1 | Day 6 | Raw search queries returned noisy irrelevant pages (blogs, gift ideas, Wikipedia) | Added 4-vector query expansion templates that constrain keywords to domain, problem, solution, and audience.
Sprint 2 | Day 4 | Sequential execution of Market and Competitor agents caused high latency (~9.5 seconds) | Refactored orchestrator to execute both agent coroutines concurrently using Python asyncio.gather().
Sprint 2 | Day 8 | Competitor analysis failed when search results were empty during offline local development | Created domain-aware synthetic competitor fallback engine in orchestrator to guarantee schema completeness.
Sprint 3 | Day 5 | Scientific empirical validation required specialized biotech & medical terms not in standard dictionary | Engineered biomedical domain taxonomy heuristics and literature citation extraction models.
Sprint 4 | Day 3 | Direct competitor classifier had false-negative classification on search results with 'Competitor' in title | Enhanced _looks_like_direct_competitor heuristic to detect explicit competitor/app signals with topic overlap.
Sprint 4 | Day 7 | Merge conflict risk between Member 1's SWOT schemas and Member 4's frontend state | Conducted ad-hoc schema pairing session, confirmed Pydantic field contracts, and successfully merged clean PR #18 into staging.

## Sprint Retrospective (4Ls)
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-03 | 2026-08-14 | Member 1 | Writing unit test assertions before coding fallback routines | Relying solely on external APIs without local mocks | Pairing on Pydantic request and response contracts | Built DuckDuckGo search fallback engine
2 | Sprint 1 | 2026-08-03 | 2026-08-14 | Member 4 | Using automated API testing tools (Postman/pytest-httpx) | Hardcoding API URLs directly inside React components | Daily standup syncs on API endpoint signatures | Implemented centralized services/api.js client
3 | Sprint 2 | 2026-08-17 | 2026-08-29 | Member 2 | Documenting TAM/SAM/SOM calculation formulas in architecture docs | Using unverified market sizing assumptions | Cross-referencing search evidence with domain heuristics | Added standardized industry market sizing taxonomy
4 | Sprint 2 | 2026-08-17 | 2026-08-29 | Member 3 | Building negative keyword filters to strip non-competitor noise | Allowing encyclopedia/gift sites to count as competitors | Extracting transparent pricing models from search results | Created IRRELEVANT_SOURCE_PHRASES blacklist
5 | Sprint 3 | 2026-08-31 | 2026-09-12 | Member 2 | Structuring regulatory pathways by global standards (GDPR/FDA/FAA) | Assuming US-only compliance frameworks | Providing empirical research citations for scientific validation | Integrated regulatory disclaimer and pathway schemas
6 | Sprint 4 | 2026-09-14 | 2026-09-25 | Member 1 | Using Gherkin Given-When-Then criteria in test function docstrings | Making late schema changes without cross-team announcements | Enforcing 100% test pass rate before opening PRs | Merged PR #18 with 59/59 automated tests passing
7 | Sprint 4 | 2026-09-14 | 2026-09-25 | Member 4 | Rendering visual severity badges (High/Med/Low) for risk items | Displaying unformatted raw JSON responses on UI | Maintaining modular React card components | Built interactive SWOT grid and Risk & Mitigation tables